## Tasks
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
1 Must Have | 01 Analyze & Design | Overall | Technical Analysis | Gather requirements and finalize project scope with RealEstateCo | 2 Consultant Technical | 5 | 7 | 10 | I don't know what this feature means -HS | 9 | 1800 | ['Scope creep', 'Lack of clarity in requirements']
1 Must Have | 03 Setup | Overall | Setup Environment + Azure | Set up development, testing, and production environments in Azure | 3 Senior Consultant Technical | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Integration issues with Azure']
1 Must Have | 04 Development | Frontend | User Interface (UI) | Design and implement responsive UI for property listings and search functionality | 0 Blended FE dev | 5 | 7 | 10 | I don't know what this feature means -HS | 9 | 1800 | ['Cross-browser compatibility issues', 'Usability challenges with search and filter functionality']
1 Must Have | 04 Development | Frontend | User Interface (UI) | Design and implement user authentication and profile management functionality | 0 Blended FE dev | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Security vulnerabilities with user authentication']
1 Must Have | 04 Development | Middleware | Authentication & Authorizations | Develop REST APIs for property listings, user profiles, and appointment details | 0 Blended MW dev | 7 | 10 | 14 | I don't know what this feature means -HS | 16 | 3200 | ['API security vulnerabilities', 'Integration issues with frontend UI']
1 Must Have | 04 Development | Middleware | Filtering / search | Implement search and filter functionality based on various criteria (price range, location, property type, etc.) | 0 Blended MW dev | 5 | 7 | 10 | I don't know what this feature means -HS | 9 | 1800 | ['Complexity of implementing multiple filter options', 'Performance issues with search functionality']
2 Should Have | 04 Development | Middleware | Notifications | Develop system for sending notifications to users about new listings, price reductions, and viewing confirmations | 0 Blended MW dev | 5 | 7 | 10 | I don't know what this feature means -HS | 9 | 1800 | ['Integration issues with messaging platform', 'User privacy concerns with notifications']
2 Should Have | 04 Development | Middleware | Appointment Scheduling System | Develop calendar integration and appointment management system for agents and users | 0 Blended MW dev | 7 | 10 | 14 | I don't know what this feature means -HS | 16 | 3200 | ['Complexity of integrating with multiple calendar systems', 'Performance issues with scheduling system']
2 Should Have | 04 Development | Security | Security Review | Conduct security review of platform and implement necessary measures to ensure compliance with relevant regulations | 4 Lead Expert | 7 | 10 | 14 | I don't know what this feature means -HS | 16 | 3200 | ['Discovering unknown security vulnerabilities', 'Cost of implementing necessary security measures']
3 Could Have | 04 Development | Middleware | Settings | Develop settings page for users to customize their preferences and notification settings | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Complexity of implementing multiple settings options', 'Usability challenges with settings page']