## Tasks
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
1 Must Have | 01 Analyze & Design | Overall | Technical Analysis | Gather requirements for frontend UI design | 1 Analyst | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Changes in requirements', 'Lack of clarity in requirements']
1 Must Have | 03 Setup | Infra | Setup Environment + Azure | Set up development, testing, and production environments in Azure | 2 Consultant Technical | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Configuring environments', 'Integration issues with other systems']
1 Must Have | 04 Development | Frontend | User Interface (UI) | Create property listing UI with search and filter functionality | 0 Blended FE dev | 4 | 5 | 6 | I don't know what this feature means -HS | 6 | 1200 | ['Integration with backend APIs', 'Performance issues with large datasets']
1 Must Have | 04 Development | Frontend | User Interface (UI) | Implement user authentication and profile management UI | 0 Blended FE dev | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Security concerns with user data', 'Complexity of user authentication flow']
1 Must Have | 04 Development | Middleware | Authentication & Authorizations | Implement secure user authentication and authorization system | 0 Blended MW dev | 4 | 5 | 6 | I don't know what this feature means -HS | 6 | 1200 | ['Security vulnerabilities', 'Integration with frontend UI']
2 Should Have | 04 Development | Middleware | Filtering / search | Implement advanced search and filtering options for property listings | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Performance issues with complex search queries', 'Integration with database']
2 Should Have | 04 Development | Middleware | Notifications | Implement user notification system for new listings and viewing confirmations | 0 Blended MW dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Integration with frontend UI', 'Notification delivery reliability']
3 Could Have | 04 Development | Middleware | Monitoring | Implement monitoring and analytics system for user engagement metrics | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Complexity of data analytics', 'Integration with database']
3 Could Have | 04 Development | Middleware | Settings | Implement user settings functionality for profile and notification preferences | 0 Blended MW dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Integration with frontend UI', 'Security concerns with user data']
3 Could Have | 04 Development | Security | Security Review | Conduct security review and penetration testing of the platform | 2 Consultant Technical | 4 | 5 | 6 | I don't know what this feature means -HS | 7 | 1400 | ['Identification of vulnerabilities', 'Integration with existing security systems']