## Tasks
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
1 Must Have | 01 Analyze & Design | Overall | Functional Analysis | Gather requirements from RealEstateCo stakeholders and create a detailed functional requirements document | 1 Analyst | 5 | 7 | 10 | I don't know what this feature means -HS | 8 | 1600 | ['Stakeholders may have conflicting requirements', 'Requirements may change during the project', 'Difficulty in prioritizing requirements']
1 Must Have | 03 Setup | Infra | Setup Environment + Azure | Set up development, testing, and production environments in Azure | 2 Consultant Technical | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Lack of familiarity with Azure', 'Difficulty in configuring environments']
1 Must Have | 04 Development | Frontend | User Authentication | Implement secure user authentication for the platform | 0 Blended FE dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Security concerns', 'Difficulty in integrating with backend system']
1 Must Have | 04 Development | Backend | Database Management | Design and develop a relational database to store property listings, user profiles, and interactions | 3 Senior Consultant Technical | 4 | 6 | 8 | I don't know what this feature means -HS | 8 | 1600 | ['Difficulty in designing a scalable database', 'Complexity in managing data relationships']
1 Must Have | 04 Development | Middleware | APIs for Data Access | Build REST APIs for accessing and updating property listings, user profiles, and appointment details | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Security concerns', 'Difficulty in integrating with frontend system']
1 Must Have | 04 Development | Frontend | Property Listings | Design and develop a UI to display property details, images, price, and location with a map integration for geolocation of properties | 0 Blended FE dev | 3 | 4 | 6 | I don't know what this feature means -HS | 6 | 1200 | ['Difficulty in integrating with map API', 'UI may not be user-friendly']
1 Must Have | 04 Development | Frontend | Search and Filter Functionality | Implement search and filter functionality to allow users to search by various filters such as price range, location, and property type | 0 Blended FE dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Complexity in implementing advanced search features', 'Difficulty in integrating with backend system']
1 Must Have | 04 Development | Middleware | User Roles and Permissions | Differentiate access levels for users (buyers, agents, admins) to control their data access and modify permissions accordingly | 1 Analyst | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Difficulty in defining user roles and permissions', 'Complexity in managing user access levels']
1 Must Have | 04 Development | Middleware | Appointment Scheduling System | Integrate a scheduling system with calendar sync options to allow users to book viewings with agents | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 5 | 1000 | ['Difficulty in integrating with calendar API', 'Complexity in managing appointment scheduling']
1 Must Have | 04 Development | Frontend | Contact and Messaging System | Enable direct communication between potential buyers and real estate agents via a secure messaging platform | 0 Blended FE dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Security concerns', 'Difficulty in integrating with messaging API']