## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
2 Should Have | 02 Architecture | Security | Authentication & Authorizations | Task: Authentication & Authorizations for Security | Fullstack Developer | 2 | 4 | 5 | 0% | 3 | 720
1 Must Have | 04 Development | Frontend | Technical Analysis | Task: Technical Analysis for Frontend | Consultant Technical | 2 | 3 | 7 | 0% | 3 | 750
1 Must Have | 01 Analyze & Design | Frontend | Security Review | Task: Security Review for Frontend | Senior Consultant Technical | 2 | 4 | 7 | 0% | 2 | 600
3 Could Have | 04 Development | Frontend | Notifications | Task: Notifications for Frontend | UI Designer | 3 | 6 | 8 | 0% | 6 | 1080
3 Could Have | 04 Development | Security | Appointment Scheduling System | Task: Appointment Scheduling System for Security | Consultant Technical | 2 | 5 | 8 | 0% | 4 | 1000
2 Should Have | 02 Architecture | Overall | Settings | Task: Settings for Overall | Lead Expert | 1 | 4 | 8 | 0% | 7 | 3500
3 Could Have | 01 Analyze & Design | Security | Technical Analysis | Task: Technical Analysis for Security | Fullstack Developer | 1 | 4 | 7 | 0% | 2 | 480
1 Must Have | 04 Development | Frontend | Security Review | Task: Security Review for Frontend | Senior Consultant Technical | 4 | 7 | 10 | 0% | 5 | 1500
2 Should Have | 04 Development | Middleware | Settings | Task: Settings for Middleware | Quality Assurance Engineer | 1 | 2 | 4 | 0% | 1 | 220
3 Could Have | 03 Setup | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | Quality Assurance Engineer | 2 | 4 | 5 | 0% | 4 | 880
2 Should Have | 01 Analyze & Design | Frontend | Authentication & Authorizations | Task: Authentication & Authorizations for Frontend | Fullstack Developer | 1 | 2 | 5 | 0% | 1 | 240
2 Should Have | 01 Analyze & Design | Overall | Technical Analysis | Task: Technical Analysis for Overall | Quality Assurance Engineer | 2 | 3 | 4 | 0% | 3 | 660
1 Must Have | 03 Setup | Overall | Filtering / search | Task: Filtering / search for Overall | Quality Assurance Engineer | 2 | 3 | 6 | 0% | 3 | 660
1 Must Have | 03 Setup | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | Fullstack Developer | 3 | 6 | 7 | 0% | 4 | 960
3 Could Have | 04 Development | Security | Setup Environment + Azure | Task: Setup Environment + Azure for Security | Lead Expert | 4 | 6 | 9 | 0% | 4 | 2000
3 Could Have | 03 Setup | Overall | Filtering / search | Task: Filtering / search for Overall | Lead Expert | 4 | 5 | 6 | 0% | 6 | 3000
2 Should Have | 02 Architecture | Overall | Security Review | Task: Security Review for Overall | UI Designer | 2 | 4 | 7 | 0% | 6 | 1080
1 Must Have | 03 Setup | Frontend | Filtering / search | Task: Filtering / search for Frontend | Blended FE dev | 4 | 6 | 7 | 0% | 7 | 1400
2 Should Have | 02 Architecture | Frontend | Appointment Scheduling System | Task: Appointment Scheduling System for Frontend | Blended MW dev | 1 | 4 | 7 | 0% | 5 | 1100
1 Must Have | 03 Setup | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | Senior Consultant Technical | 2 | 5 | 8 | 0% | 2 | 600 | ['Scope creep']