## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
1 Must Have | 03 Setup | Security | Setup Environment + Azure | Task: Setup Environment + Azure for Security | Blended MW dev | 3 | 6 | 9 | 0% | 4 | 880
2 Should Have | 03 Setup | Overall | User Interface (UI) | Task: User Interface (UI) for Overall | Blended FE dev | 3 | 6 | 9 | 0% | 5 | 1000
1 Must Have | 02 Architecture | Security | Appointment Scheduling System | Task: Appointment Scheduling System for Security | Fullstack Developer | 1 | 4 | 7 | 0% | 6 | 1440
3 Could Have | 04 Development | Frontend | Security Review | Task: Security Review for Frontend | Consultant Technical | 1 | 4 | 8 | 0% | 3 | 750
1 Must Have | 01 Analyze & Design | Security | Technical Analysis | Task: Technical Analysis for Security | Quality Assurance Engineer | 4 | 5 | 8 | 0% | 4 | 880
3 Could Have | 04 Development | Frontend | Filtering / search | Task: Filtering / search for Frontend | Blended MW dev | 2 | 4 | 8 | 0% | 5 | 1100
3 Could Have | 02 Architecture | Frontend | Setup Environment + Azure | Task: Setup Environment + Azure for Frontend | Quality Assurance Engineer | 3 | 6 | 10 | 0% | 3 | 660
3 Could Have | 02 Architecture | Overall | Notifications | Task: Notifications for Overall | Consultant Technical | 4 | 5 | 8 | 0% | 4 | 1000
3 Could Have | 04 Development | Overall | Technical Analysis | Task: Technical Analysis for Overall | Consultant Technical | 4 | 5 | 8 | 0% | 7 | 1750
1 Must Have | 03 Setup | Middleware | Security Review | Task: Security Review for Middleware | Consultant Technical | 4 | 7 | 9 | 0% | 5 | 1250
1 Must Have | 03 Setup | Overall | Settings | Task: Settings for Overall | Blended MW dev | 4 | 7 | 9 | 0% | 9 | 1980 | ['Integration issues with Azure']
2 Should Have | 04 Development | Middleware | Settings | Task: Settings for Middleware | Project Manager | 2 | 4 | 7 | 0% | 2 | 800
1 Must Have | 04 Development | Overall | Security Review | Task: Security Review for Overall | Lead Expert | 3 | 5 | 7 | 0% | 4 | 2000
3 Could Have | 01 Analyze & Design | Middleware | Notifications | Task: Notifications for Middleware | Lead Expert | 3 | 6 | 8 | 0% | 4 | 2000
2 Should Have | 02 Architecture | Middleware | Setup Environment + Azure | Task: Setup Environment + Azure for Middleware | Quality Assurance Engineer | 4 | 5 | 8 | 0% | 5 | 1100
1 Must Have | 03 Setup | Middleware | Filtering / search | Task: Filtering / search for Middleware | Blended FE dev | 2 | 3 | 5 | 0% | 5 | 1000
1 Must Have | 02 Architecture | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | UI Designer | 1 | 2 | 4 | 0% | 2 | 360
2 Should Have | 03 Setup | Middleware | Setup Environment + Azure | Task: Setup Environment + Azure for Middleware | Project Manager | 1 | 2 | 5 | 0% | 1 | 400
2 Should Have | 02 Architecture | Security | Authentication & Authorizations | Task: Authentication & Authorizations for Security | Blended FE dev | 3 | 6 | 7 | 0% | 4 | 800