## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
1 Must Have | 04 Development | Overall | Appointment Scheduling System | Task: Appointment Scheduling System for Overall | Lead Expert | 4 | 6 | 8 | 0% | 5 | 2500
2 Should Have | 01 Analyze & Design | Middleware | User Interface (UI) | Task: User Interface (UI) for Middleware | Blended MW dev | 2 | 3 | 7 | 0% | 7 | 1540
1 Must Have | 01 Analyze & Design | Security | Settings | Task: Settings for Security | Consultant Technical | 1 | 3 | 6 | 0% | 3 | 750
1 Must Have | 03 Setup | Middleware | Setup Environment + Azure | Task: Setup Environment + Azure for Middleware | Consultant Technical | 2 | 3 | 6 | 0% | 3 | 750
3 Could Have | 04 Development | Overall | User Interface (UI) | Task: User Interface (UI) for Overall | Fullstack Developer | 3 | 6 | 9 | 0% | 6 | 1440
1 Must Have | 01 Analyze & Design | Frontend | Authentication & Authorizations | Task: Authentication & Authorizations for Frontend | Quality Assurance Engineer | 3 | 6 | 10 | 0% | 3 | 660
3 Could Have | 02 Architecture | Middleware | Settings | Task: Settings for Middleware | UI Designer | 4 | 7 | 9 | 0% | 7 | 1260
1 Must Have | 03 Setup | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | Blended MW dev | 2 | 5 | 8 | 0% | 5 | 1100
2 Should Have | 04 Development | Frontend | Settings | Task: Settings for Frontend | Quality Assurance Engineer | 3 | 6 | 8 | 0% | 3 | 660