## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
2 Should Have | 01 Analyze & Design | Security | Security Review | Task: Security Review for Security | UI Designer | 2 | 4 | 5 | 0% | 4 | 720
3 Could Have | 02 Architecture | Frontend | Technical Analysis | Task: Technical Analysis for Frontend | Blended MW dev | 1 | 3 | 7 | 0% | 5 | 1100 | ['Cross-browser compatibility issues']
1 Must Have | 04 Development | Security | Technical Analysis | Task: Technical Analysis for Security | UI Designer | 1 | 3 | 5 | 0% | 3 | 540
3 Could Have | 01 Analyze & Design | Overall | Notifications | Task: Notifications for Overall | Blended MW dev | 1 | 2 | 5 | 0% | 5 | 1100
1 Must Have | 01 Analyze & Design | Security | Filtering / search | Task: Filtering / search for Security | Project Manager | 1 | 3 | 5 | 0% | 3 | 1200
1 Must Have | 02 Architecture | Frontend | Setup Environment + Azure | Task: Setup Environment + Azure for Frontend | Blended MW dev | 2 | 4 | 6 | 0% | 5 | 1100
2 Should Have | 01 Analyze & Design | Security | Filtering / search | Task: Filtering / search for Security | Quality Assurance Engineer | 2 | 3 | 7 | 0% | 7 | 1540
2 Should Have | 01 Analyze & Design | Middleware | Notifications | Task: Notifications for Middleware | Blended MW dev | 1 | 3 | 7 | 0% | 3 | 660
2 Should Have | 03 Setup | Overall | Settings | Task: Settings for Overall | Fullstack Developer | 3 | 6 | 10 | 0% | 7 | 1680
2 Should Have | 04 Development | Overall | User Interface (UI) | Task: User Interface (UI) for Overall | Fullstack Developer | 3 | 4 | 5 | 0% | 4 | 960
2 Should Have | 04 Development | Overall | Appointment Scheduling System | Task: Appointment Scheduling System for Overall | Project Manager | 1 | 4 | 7 | 0% | 5 | 2000