## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
3 Could Have | 02 Architecture | Frontend | Appointment Scheduling System | Task: Appointment Scheduling System for Frontend | UI Designer | 4 | 6 | 10 | 0% | 8 | 1440
3 Could Have | 01 Analyze & Design | Security | Settings | Task: Settings for Security | Consultant Technical | 4 | 6 | 8 | 0% | 6 | 1500
2 Should Have | 04 Development | Middleware | Authentication & Authorizations | Task: Authentication & Authorizations for Middleware | Consultant Technical | 3 | 4 | 8 | 0% | 4 | 1000
1 Must Have | 02 Architecture | Frontend | Settings | Task: Settings for Frontend | Consultant Technical | 4 | 6 | 9 | 0% | 5 | 1250
2 Should Have | 03 Setup | Security | Settings | Task: Settings for Security | Blended MW dev | 4 | 6 | 8 | 0% | 8 | 1760
3 Could Have | 02 Architecture | Security | Notifications | Task: Notifications for Security | Blended FE dev | 3 | 6 | 7 | 0% | 7 | 1400
3 Could Have | 03 Setup | Middleware | User Interface (UI) | Task: User Interface (UI) for Middleware | Quality Assurance Engineer | 4 | 6 | 9 | 0% | 4 | 880
1 Must Have | 03 Setup | Frontend | Filtering / search | Task: Filtering / search for Frontend | Senior Consultant Technical | 1 | 2 | 3 | 0% | 2 | 600
3 Could Have | 01 Analyze & Design | Security | Technical Analysis | Task: Technical Analysis for Security | Consultant Technical | 2 | 3 | 4 | 0% | 3 | 750
1 Must Have | 02 Architecture | Security | Authentication & Authorizations | Task: Authentication & Authorizations for Security | Lead Expert | 3 | 5 | 9 | 0% | 5 | 2500
3 Could Have | 03 Setup | Security | Setup Environment + Azure | Task: Setup Environment + Azure for Security | Blended FE dev | 4 | 5 | 8 | 0% | 8 | 1600 | ['Security vulnerabilities']
2 Should Have | 03 Setup | Middleware | Notifications | Task: Notifications for Middleware | Lead Expert | 3 | 6 | 7 | 0% | 3 | 1500