## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
3 Could Have | 04 Development | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | Project Manager | 2 | 5 | 9 | 0% | 4 | 1600
1 Must Have | 02 Architecture | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | Blended FE dev | 2 | 4 | 7 | 0% | 5 | 1000
1 Must Have | 03 Setup | Security | User Interface (UI) | Task: User Interface (UI) for Security | UI Designer | 3 | 5 | 8 | 0% | 4 | 720
2 Should Have | 03 Setup | Middleware | Security Review | Task: Security Review for Middleware | Blended FE dev | 1 | 2 | 5 | 0% | 2 | 400
2 Should Have | 04 Development | Security | Notifications | Task: Notifications for Security | Project Manager | 4 | 6 | 9 | 0% | 5 | 2000
2 Should Have | 01 Analyze & Design | Overall | Technical Analysis | Task: Technical Analysis for Overall | Quality Assurance Engineer | 4 | 5 | 9 | 0% | 6 | 1320
1 Must Have | 03 Setup | Frontend | Notifications | Task: Notifications for Frontend | Lead Expert | 3 | 5 | 7 | 0% | 5 | 2500
3 Could Have | 02 Architecture | Overall | Authentication & Authorizations | Task: Authentication & Authorizations for Overall | Project Manager | 2 | 5 | 9 | 0% | 5 | 2000
3 Could Have | 03 Setup | Security | Authentication & Authorizations | Task: Authentication & Authorizations for Security | Senior Consultant Technical | 2 | 5 | 9 | 0% | 4 | 1200