## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
1 Must Have | 01 Analyze & Design | Overall | Settings | Task: Settings for Overall | Blended MW dev | 1 | 4 | 5 | 0% | 2 | 440
3 Could Have | 04 Development | Overall | Filtering / search | Task: Filtering / search for Overall | Blended MW dev | 4 | 5 | 6 | 0% | 4 | 880
1 Must Have | 02 Architecture | Frontend | User Interface (UI) | Task: User Interface (UI) for Frontend | Blended FE dev | 4 | 7 | 10 | 0% | 6 | 1200
2 Should Have | 04 Development | Overall | Filtering / search | Task: Filtering / search for Overall | Project Manager | 4 | 6 | 7 | 0% | 6 | 2400
2 Should Have | 04 Development | Security | Settings | Task: Settings for Security | Consultant Technical | 1 | 3 | 6 | 0% | 1 | 250
1 Must Have | 04 Development | Frontend | User Interface (UI) | Task: User Interface (UI) for Frontend | Consultant Technical | 1 | 3 | 6 | 0% | 2 | 500
3 Could Have | 02 Architecture | Middleware | Notifications | Task: Notifications for Middleware | Lead Expert | 2 | 4 | 6 | 0% | 4 | 2000
2 Should Have | 04 Development | Overall | Security Review | Task: Security Review for Overall | Project Manager | 4 | 6 | 10 | 0% | 10 | 4000
3 Could Have | 01 Analyze & Design | Middleware | Notifications | Task: Notifications for Middleware | UI Designer | 4 | 6 | 9 | 0% | 5 | 900
3 Could Have | 04 Development | Frontend | User Interface (UI) | Task: User Interface (UI) for Frontend | UI Designer | 1 | 2 | 4 | 0% | 1 | 180 | ['Integration issues with Azure']