## Sheet1
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
3 Could Have | 03 Setup | Security | User Interface (UI) | Task: User Interface (UI) for Security | Quality Assurance Engineer | 2 | 4 | 7 | 0% | 7 | 1540
2 Should Have | 02 Architecture | Middleware | Appointment Scheduling System | Task: Appointment Scheduling System for Middleware | Lead Expert | 2 | 3 | 7 | 0% | 2 | 1000
2 Should Have | 04 Development | Frontend | Technical Analysis | Task: Technical Analysis for Frontend | Quality Assurance Engineer | 2 | 3 | 4 | 0% | 4 | 880
3 Could Have | 01 Analyze & Design | Overall | Setup Environment + Azure | Task: Setup Environment + Azure for Overall | Quality Assurance Engineer | 3 | 5 | 6 | 0% | 6 | 1320
2 Should Have | 01 Analyze & Design | Middleware | Technical Analysis | Task: Technical Analysis for Middleware | Project Manager | 4 | 5 | 6 | 0% | 5 | 2000
2 Should Have | 04 Development | Middleware | Notifications | Task: Notifications for Middleware | Blended FE dev | 2 | 3 | 4 | 0% | 4 | 800
2 Should Have | 01 Analyze & Design | Overall | Settings | Task: Settings for Overall | Fullstack Developer | 1 | 2 | 5 | 0% | 5 | 1200
3 Could Have | 03 Setup | Frontend | Appointment Scheduling System | Task: Appointment Scheduling System for Frontend | Fullstack Developer | 2 | 4 | 7 | 0% | 2 | 480
3 Could Have | 04 Development | Middleware | Authentication & Authorizations | Task: Authentication & Authorizations for Middleware | Project Manager | 1 | 3 | 6 | 0% | 6 | 2400