## Tasks
MSCW | Area | Module | Feature | Task | Profile | MinDays | RealDays | MaxDays | Contingency | EstimatedDays | EstimatedPrice | potential_issues
1 Must Have | 01 Analyze & Design | Overall | Technical Analysis | Conduct a technical analysis to determine the best technologies and infrastructure for the project | 2 Consultant Technical | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Integration issues with legacy systems']
1 Must Have | 03 Setup | Infra | Setup Environment + Azure | Set up environments for development, testing, and production on Azure | 0 Blended Overall dev | 1 | 2 | 3 | I don't know what this feature means -HS | 3 | 600 | ['Configuration issues with Azure']
1 Must Have | 04 Development | Frontend | User Interface (UI) | Design and develop a responsive UI that provides a seamless experience across devices | 0 Blended FE dev | 3 | 4 | 5 | I don't know what this feature means -HS | 6 | 1200 | ['Cross-browser compatibility issues']
1 Must Have | 04 Development | Middleware | Authentication & Authorizations | Implement secure user authentication to allow users to save favorite listings and schedule appointments | 0 Blended MW dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Security vulnerabilities']
1 Must Have | 04 Development | Middleware | Filtering / search | Develop search and filter functionality based on various criteria such as price range, location, property type, and number of bedrooms | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 6 | 1200 | ['Performance issues with large amounts of data']
1 Must Have | 04 Development | Middleware | Notifications | Develop a system for sending notifications to users and admins, such as new listings in their preferred area or viewing confirmations | 0 Blended MW dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Integration issues with messaging system']
1 Must Have | 04 Development | Middleware | APIs for Data Access | Build REST APIs for accessing and updating property listings, user profiles, and appointment details | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 6 | 1200 | ['Security vulnerabilities']
1 Must Have | 04 Development | Middleware | Appointment Scheduling System | Integrate a scheduling system with calendar sync options to allow users to book viewings with agents | 0 Blended MW dev | 2 | 3 | 4 | I don't know what this feature means -HS | 4 | 800 | ['Integration issues with calendar systems']
1 Must Have | 04 Development | Backend | Listing Management | Develop tools for managing property listings, including adding, updating, and removing listings, with options for bulk actions | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 6 | 1200 | ['Performance issues with large amounts of data']
1 Must Have | 04 Development | Backend | Analytics & Reporting | Display statistics on user engagement and generate reports on a weekly or monthly basis | 0 Blended MW dev | 3 | 4 | 5 | I don't know what this feature means -HS | 6 | 1200 | ['Data accuracy issues']